## Gantt Chart
System Name | Student Attendance Management System
Members: | Harvey Mata
Harold Vince Mata
Jenette Ephan
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September | [29 empty] | October | [30 empty] | November | [30 empty] | December
Tasks | Assignee | Date Started | Date Finished | Status | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1. User Authentication - Registration | Harvey and Harold Mata
1.1 Design Registration Form |  | 2024-09-20 | 2024-10-04 | In-Progess
1.2 Implement the registration page |  | 2024-09-20 | 2024-10-04 | Todo
1.3 Integrate with database |  | 2024-09-20 | 2024-10-04 | Todo
1.4 Test Registration Process |  | 2024-10-05 | 2024-10-18 | Todo
2. User Authentication - Log in | Jenette Ephan
2.1 Design Login Form |  | 2024-09-20 | 2024-10-04 | In-Progess
2.2 Implement the login page |  | 2024-09-20 | 2024-10-04 | Todo
2.3 Integrate with database |  | 2024-09-20 | 2024-10-04 | Todo
2.4 Test Registration Process |  | 2024-10-04 | 2024-10-18 | Todo
3. User Authentication - Log out | Harvey Mata
3.1 Design Logout Functionality |  | 2024-09-20 | 2024-10-04 | In-Progess
3.2 Implement Logout logic |  | 2024-10-01 | 2024-10-04 | Todo
3.3 Update Frontend to Handle Logout |  | 2024-10-01 | 2024-10-04 | Todo
3.4 Test Logout Process |  | 2024-10-08 | 2024-10-11 | Todo
4. Class Management | Jenette Ephan
4.1 Design Class Management Interface |  | 2024-09-20 | 2024-10-04 | In-Progess
4.2 Implement Frontend for Class Creation/Editing |  | 2024-10-05 | 2024-10-25 | Todo
4.3 Set up Backend API for Class Management |  | 2024-10-05 | 2024-10-25 | Todo
4.4 Integrate Frontend with Backend |  | 2024-10-05 | 2024-10-25 | Todo
5. Student Management | Harold Vince Mata
5.1 Design Student Management Interface |  | 2024-09-28 | 2024-10-04 | In-Progess
5.2 Implement Frontend for Student Creation/Editing |  | 2024-09-28 | 2024-10-04 | Todo
5.3 Set up Backend API for Student Management |  | 2024-09-28 | 2024-10-04 | Todo
5.4 Integrate Frontend with Backend |  | 2024-09-28 | 2024-10-04 | Todo
5.5 Test Student Management Functionality |  | 2024-10-05 | 2024-10-18 | Todo
6. Real-time Attendance Tracking | Jenette Ephan
6.1 Design Real-time Attendance Interface |  | 2024-10-21 | 2024-10-02 | In-Progess
6.2 Implement Frontend for Attendance Tracking |  | 2024-10-22 | 2024-10-02 | Todo
6.3 Set up Backend API for Attendance Tracking |  | 2024-10-23 | 2024-10-02 | Todo
6.4 Integrate Real-time Features (WebSocket, etc.) |  | 2024-10-24 | 2024-10-02 | Todo
6.5 Test Real-time Attendance Tracking |  | 2024-10-28 | 2024-11-08 | Todo
7. Attendance Report | Harold Vince Mata
7.1 Design Attendance Report Layout |  | 2024-10-28 | 2024-11-08 | In-Progess
7.2 Implement Report Generation Logic |  | 2024-10-28 | 2024-11-08 | Todo
7.3 Set up Backend API for Report Retrieval |  | 2024-10-28 | 2024-11-08 | Todo
7.4 Integrate Frontend with Report API |  | 2024-10-28 | 2024-11-08 | Todo
7.5 Test Report Generation |  | 2024-11-11 | 2024-11-29 | Todo
8. Import/Export Data | Harvey Mata
8.1 Design Import/Export Interface |  | 2024-10-28 | 2024-11-08 | In-Progess
8.2 Implement Data Parsing Logic |  | 2024-10-28 | 2024-11-08 | Todo
8.3 Set up Backend API for Import/Export |  | 2024-10-28 | 2024-11-08 | Todo
8.4 Integrate Frontend with Import/Export Features |  | 2024-10-28 | 2024-11-08 | Todo
8.5 Test Import/Export Functionality |  | 2024-11-11 | 2024-11-29 | Todo
9. Account Settings | Harvey Mata
9.1 Design account settings interface |  | 2024-12-01 | 2024-12-13 | In-Progess
9.2 Implement Frontend with Backend |  | 2024-12-01 | 2024-12-06 | Todo
9.3 Set up Backend API for Account Management |  | 2024-12-01 | 2024-12-06 | Todo
9.4 Integrate Frontend with Backend |  | 2024-12-01 | 2024-12-06 | Todo
9.5 Test Account Settings Functionality |  | 2024-12-09 | 2024-12-13 | Todo